## Guidelines
Guidelines
Sr # | Description
1 | Pictorial Evidences of CME Works and BOQ shall be collected
2 | OTDR Traces shall be recorded for at least 2 Fiber Pairs per Link
3 | NOC Data Shall be verified on Site
4 | In case any if any of the Task is not completed, reason of the same should be mentioned and provide pictorial evidence
5 | Deployed BoQ detail shall be verified on site and submitted.

## Civil work
Inspection of OSP Civil Work.
Test Items | Test Sub-items | Description | YES/NO | Details
Civil Work | Trench | Trench depth achieved. [standard depth 1.5m] (may vary according to conditions.)
Warning Tape
Protection Bricks or HDPE pipe laid
Cable Loop available
No Water in the Trench
Duct Entry to HH/MH: Verify Clearance From Floor and Extension of Ducts into Manhole
Backfilling of Trench
Trench bed leveled
Compaction of Backfill
Handhole Inspection | Handhole | Cable Loop available
Both side Route Labeling on OFC
Cable Placed in Correct Formation Parallel to the ground
Joint Box Properly Placed
Both side Route Labeling on OFC
HH/Jp Cover/slab properly placed
Handholes are installed at right dimensions in terms of (W*L*D)
HH are propely cleaned and brackets are correctly placed for the closures
Spice enclosure properly placed and selected secured
OFC Inspection | Cable Exposure | Cable exposed at transition points or along route
| Cable Bends | Cable Bend radius violated (not more then 45 degrees)
| cable slack | slack storage provided
cable covered by sand or split duct
| Splice Closures | Splice Locations checked for sheath marks, cable bends etc
Joint Enclosure Test | Enclosure | Physical Damage present on the enclosures
cable entries sealed (heat shrink tubes or Gasket Material)
Fiber organizer cassettes securely positioned
Enclosure tightness as per standard
| Fiber Organizer Cassettes | Enough fiber left on either side of splice in the cassette (Standard = 1.5m)
All Fibres Fusion Spliced and Monitored and Recorded.The Average Splice Loss at 1550 nm Accord GOP/Huawei Specifications.
Fibre And Cable Labeling Co mpleted As Per GOP/Huawei Specifications
Splice Enclosure Sealed and Mounted in the Manhole
| Fiber Splice Protectors | Residual force in fiber due to protector
Inspection | Link Inspection | Hand hole with slack fiber marked (as per As built Drawing), Link Routes (as per diagram)
Hand hole with joint Enclosure marked (e.g two route indicators), building entry point from zero manholedemarcated.
Remarks: SIGNATURES:

## Aerial Cable
Aerial Deployments Checklist
S/NO | Description (Service effecting Items) | Remarks
1 | Check the quality of existing and new poles on which aerial cable is deployed
2 | Lashing of cable is done with the support strand (Y/N).
3 | Span length is 50% in case of over-lashed cable on existing cable (Y/N).
4 | Clearance of aerial cable from ground is minimum 6 meters (Y/N).
5 | Clearance between electrical and fiber cable is minimum 50”(Y/N).
6 | Strength of poll is enough to carry fiber cable load for minimum 20 years(Y/N).
7 | Enough spare cable is length at each end of the polls for cable pulling and future splicing (Y/N).
8 | From HH/Site to poll cable is pulled in GI pipe (Y/N).
9 | Cable is clear off any vegetation(Y/N).
10 | There is no unnecessary road crossing (Y/N).
11 | In case of road crossing the clearance from ground shall be 9 meter (Y/N).
Remarks: SIGNATURES:

## Fiber
Site Name: - ______________ |  | Date: ____________________
Site ID: - _______________ |  | TA :- ____________________
Fiber Cable Checklist
S/NO | Description (Service effecting Items) | YES / No | Remarks
1 | Cabinet has the right ID (Node name and code)
2 | All Cards in the cabinet are installed and properly indentified
3 | Ensure that fiber cable are installed and labeled with the proper ID
4 | The fiber in trays are correctly installed
5 | Splitter are installed in tray
6 | ODFs have a warning label placed on the main cover
7 | Every fiber has been individully indentified
8 | ODF output fibers with the splitter are clearly marked
9 | All Fiber pairs are having power and losses
10 | Does fiber Implementation related material is as per received BOQ from USF
11 | All fiber tests meet USF specifications for power and loss (OTDR, Power Meter, etc).
12 | Ensure that protection posts are installed properly as per standards

## ISP
Physical Inspection Checklist
Test Items | Test Sub-items | Description | YES/NO | Details
Rack | Installations | Rack Properly Mounted
| Cable routing | Cable Bend Radius violated (check at duct entrances, ladder racks, etc)
Cable deformed
Any rigid components (central members, rods, armour etc) can damage fibers in case of mechanical agitation
Cable ends properly terminated
ODF | Splice trays | Splice trays complying to standards
Splice secured properly
Splice protected properly
Fibers routed properly in the splice tray
| Connectors | Connectors properly installed
Violation of bend radius of connecting fibers inside ODF
Fiber Under Tension
Labeling Provided
System | Capacity | GPON Cards (control cards & PON cards)
Optical power level.(GPON)
Onsite User testing (voice, unicast & multicast service verification)
System Capacity (STM)
Optical Interface Cards
DDF Rack Capacity
Alarms | External Alarms | Commercial
Solar
Genset
Rectifier
AC / Temperature
Humidity
DG low fuel
Remarks: SIGNATURES:

## CME
Mechanical & Electrical Works Checklist
Test Item | Test | YES/NO | Details
Engine Generator | Engine Capacity
Cleanliness
Fuel Routing Arrangement (Safety First)
Spare Fuel tank (Capacity)
Control Panel
Exhaust/ Ventilation system
Starting Battery(Capacity)
Rectifier | Rectifier Make/ Model
No. of Rectifier Modules
Capacity
Battery Bank | Installation Capacity
Type/ Make
Cell Capacity (Ah)
No. of total Cells
Terminal Voltage
Solar Panels(where applicable) | Total Panel Capacity
Panel Fixture
Battery Charging Module
Building | Paint condition
Boundary wall with barbed wire
Cleanliness
Levelling
Tower | Physical inspection (paint, galvanization, structure)
All tower legs looped and earthed
Tower loading (number of microwave dishes and RF Antennas)
Earthing | Resistance of Main Earth
Earth lead fixing (Earth Main Connector)
Main rack ground
All external AC cables are enclosed in conduit of the correct type and routed/clamped properly.
Misc | All switches, sockets, lights/emergency lights are installed and functioning correctly.
The outdoor security lights are installed in relevant areas and are operating.
Commercial Power | Independent
Shared
Meter Type
Transformer Capacity
Net Load of the site
Capacity Available
COMMENTS: SIGNATURES:

## Insertion loss test
Insertion Loss Test
Section: ____________________ |  |  |  |  | Date: _____________
A-End: ____________________ |  |  |  |  | B-End: _____________
Fiber No: | 1310/1550nm |  | A | 1310/1550nm |  | B | Average Loss
| TX (db) | RX (db) | Section Loss | TX (db) | RX (db) | Section Loss
1
2
3
4
Requirements |  |  |  |  | 1550nm | 1310nm
Cable Attenuation Per km |  |  |  |  | 0.25 | 0.38
Total Physical Cable Length (km): |  |  |  |  | 0 | 0
Average Attenuation : |  |  |  |  | 0.22 | 0.35
Maximum Splice Loss : |  |  |  |  | 0.05 | 0.05
Maximum Connector Loss |  |  |  |  | 0.5 | 0.5
Total Section Loss:
Signatures of SP and USF: _________________

## OTDR Test
OTDR Test Results
Section: ____________________ |  |  |  |  | Date: _____________
A-End: ____________________ |  |  |  |  | B-End: _____________
| Fiber No: | Trace Taken | length (Km) | Loss (dB)
1
2
3
4
*Minumum 2 pairs of Dark Fiber shall be tested using OTDR
Signatures of SP and USF: _________________
Name
Designation

## Health and Safety
Health and safety Checklist
S/NO | Description (Service effecting Items) | YES / No | Remarks
1 | All staff trained, qualified and experienced
2 | Verify safe cable handling and testing practices
3 | Cables disposed of in a safe and responsible manner
4 | No negative environmental impacts
5 | All materials type tested and approved
6 | All equipment and tools approved, tested and certified as appropriate
7 | Warning signs, barricades in place as required
8 | Manhole clean and free of water
9 | Cable bearers installed
10 | Cable ends prepared for splicing